IT Project and Quality Management

COMP1305 Coursework

Student Name: Duong Bui Dinh

Student Roll Number: GT00010

Instructor: Thang Hoang Viet

Contents

Introduction	3

Current Problem	3

Problem Solving	5

Project Strategies	6

Result of project	8

Appendix A-Spread sheet Model	9

Weighted Scoring Model (WSM)	9

Test Requirement	19

Test Plan	20

Test log	23

Appendix B- Presentation	32

Appendix C- WBS	42

Project Roles & Responsibilities	42

Work Breakdown Structure Dictionary	43

WBS Scenario	49

WBS Details	50

WBS Network Diagram	52

WBS Critical Path	53

Project Resource Cost	55

References	57

# Introduction

## Current Problem

An international company, staffs currently use many types of phone, so it is difficult to manage. Many types of phone do not meet the needs of company. It is constant contact with head office.

Constant Contact means: All staffs can contact with Head Office every time and everywhere they want via network using Email, MMS, SMS, Internet, Video conferences …

Figure 1: Current problem scenario in company

## Problem Solving

A Manager has been tasked to select a type of smartphone and implement for all four hundred staffs in the company over the period of month.  This project has to solve the current problems of company: Constant Contact and Synchronization of phone for all staffs.

Figure 2: Problems are solved

## Project Strategies

What must be achieved in the project?

The Manager in this project should think about this question before starting the project. This project will be successful if it meets the following requirements

- A smartphone type meets needs of functionality (company requirement)

  - The smart phone type has to provides enough functionalities in order to keep constant contact between all staffs and Head Office

- A smartphone type is the best of finance

  - The selected smart phone takes minimum money to maintained and upgrade

- A smartphone type pleases most of all staffs

  - Staffs will directly use this smart phone , so make sure that it meets staff requirements

How to achieve the requirements?

- A smartphone type meets needs of functionality.

In order to solve this requirement, the project manager has to know what functions smart phone has to have to keep constant contact between Staffs and Head Office. Based on these functions, he/she will determine the hardware and software requirement for smart phone.

- A smartphone type is the best of finance.

The smart phone will be selected must be the answer for:

- Is it the best choice with minimum cost to maintain?

- Is it the best choice with minimum cost to upgrade?

The manager must identify all things that affect to cost for maintaining and upgrading.

Maintaining can be understood with mean: cost to use, repair. Maintaining can be understood with mean: cost to upgrade both hardware and software. So, the project manager must calculate Total Cost of Ownership to select a phone.

- A smartphone type pleases most of all staffs

Why the smart phone will be selected has to please most of all staff?

The staffs directly use this smart phone 24/7. So, the project manager should imagine he/she is a staff too.

What do the staffs want from the smart phone?

Why the project manager must care this question! The answer is “Make the smart phone more useful”. The reason is here, staffs usually work eight hours per day and adding the time they really contact with the Head Office outside the working time, assume that is one more hour.

What about other free time? The staffs have fifteen hours which is not for work (in fact it is bigger)

So, the staffs can use smart phone at that time. For example, they want to play games, record videos, capture photos....so, the smart phone should support some multimedia functions. After reducing stress, staffs works better.

The project manager should make survey to get ideas from staffs when selecting smart phone.

## Result of project

Figure 3: HTC Thunderbolt 4G will be selected

Recommended Phones: These four smartphone types in this comparison is the result after doing survey from all staffs in company.

After executing the project plan (see Appendix C) and doing WSM (see Appendix A Appendix A), HTC Thunderbolt 4G is the result of Smart Phone Selection Project.

HTC Thunderbolt 4G is the best choice because:

- It met requirement of functionality

- The total cost of ownership is the best.

  - Cheap cost for upgrading software and easy to upgrade

- The HTC Thunderbolt 4G use Android OS, which is the most popular smart phone OS.

- The software market is the biggest

- Free trend of software development

- Cheap cost for upgrading hardware

- Price of hardware peripheral is cheap

# Appendix A-Spread sheet Model

## Weighted Scoring Model (WSM)

| Requirement | Factor | Criteria | Description |
| --- | --- | --- | --- |
| Hardware requirement | Design | Phone Style | The phone needs a nice design, easy to use with many colours type to chose |
|  |  | Display Revolution | The revolution should be a high level |
|  |  | Screen size | The screen size should be between 3-4 inches |
|  |  | Weight | the phone should not weighted |
|  |  | Height | The phone should not too high |
|  | Multimedia | Camera | The camera should have a good quality , it is about 5MP or above |
|  |  | Video recorder & Quality | The phone has to support video recorder with good quality |
|  |  | Email | The phone has to support using email |
|  |  | Digital Player | The phone should support digital player |
|  |  | Sound Quality | the phone must have good quality |
|  | Call Features & Quality | 3 way calling | The phone has can converse between the cell phone user and two other parties |
|  |  | Cold holder | The phone can place a call on hold without losing the connection. |
|  |  | Signal capturing | the ability of capturing the signal from signal service provider |
|  | Battery Life & Memory & Processor | Installed Memory | The phone should have at least 8Gb of Memory |
|  |  | RAM | The phone should have at least 512Mb of Ram |
|  |  | Extendable Memory | The phone should have Extendable memory |
|  |  | Standby Time | The phone should have a long standby time. |
|  |  | Talk time | The phone should has long talk time |
|  |  | Processor speed | The phone has to have a strong processor, it is about 1Ghz |
|  | Connectivity | Wifi | The phone has to support Wifi |
|  |  | GPRS | The phone has to support GPRS |
|  |  | 4G | The phone has to support 3G,4G |
|  |  | Bluetooth | The phone should support Bluetooth |
|  |  | EDGE | The phone should support EDGE |
| Software requirement | Software & Applications | free software market | The phone should be developed in most popular software market |
|  |  | commercial software market | The phone should be developed in most popular software market |
|  |  | Office softwares | The phone support many office softwares |
|  |  | Internet browser | The phone has to support internet browser |
|  | Total Cost of Ownership | Additional Cost | Additional cost includes : Guarantee cost, Upgrade Software cost, Upgrade Hardware cost |
|  |  | One-Time Cost | The cost which has to pay only one time. For example : Purchase cost |
|  |  | Monthly Cost | Cost to maintain phone in a month |

Table 1: describes all Factors and Criteria

# Notes: Smart phones Information is used to support for WSM (see References

Figure 4: Details of spread sheet model for WSM – part 1

Figure 5: Details of spread sheet model for WSM – part 2

Figure 6: Details of spread sheet model for WSM – part 3

Figure 7: TCO in one year term calculation (without Additional Cost)

In the TCO above, the project manager don’t put Additional Cost because it is very difficult to calculate exactly. So, the Project manager wants to analyse Additional Cost in order to determine the final smart phone to buy.

If we look at TCO above, it is not really true if we select a smart phone right now, because the total prices are nearly the same.

- Additional Cost Analysis

Additional Cost is a part of Total Cost of Ownership, it includes: Guarantee cost, Hardware upgrade and Software upgrade.

Figure 8 Price of each Smart Phone

Firstly, we focus on Guarantee Cost. Guarantee Cost depends on how often the smart phone breaks down, in other word; it is quality of the product. The Guarantee Cost also depends on the Guarantee price of the smart phone vendor. In fact, all vendors are providing very good services for customer. The quality of each smart phone here are also similar each other because all manufacturers have checked the quality for each product. Therefore, in this Guarantee Cost Criteria, we can assume that all smart phones are similar.

Secondly, we move to Hardware upgrade. We can see the price of iPhone 4 and BlackBerry are expensive. As a result, we can determine the level of cost when upgrading hardware peripheral for each smart phone. The most expensive is iPhone, then BlackBerry 9900, HTC Thunderbolt 4G and Nokia N8. But the different between HTC Thunderbolt 4G and Nokia N8 is very small.

Figure 9: OS of each Smart Phone

Finally, we will analyse the Software Upgrade criteria. Each type of smart phone here uses a different Operating System. Each of OS has particular software market of its own.

We should research the application market for each type of smart phone in order to know what the best software market is.

The software market relates to Software Upgrading of smart phone in the future. When upgrading software, we want the software market is big, especially for free software.

Figure 10: Smart Phone OS Market Share (Wikipedia 2011)

As we can see the figure 10, the Android OS is most popular OS for smartphone.

There are many manufacturers combine their smart phone products with Android OS.

The android software market is free trend. It is very good.

After Android that is Symbian OS, Apple iOS.BlackBerry6 OS has very small market.

Now, we will research the free software market for each smart phone.

| Application Store | Percent Free Applications |
| --- | --- |
| Android Market (HTC Thunderbolt 4G) | 67% |
| BlackBerry App World( BlackBerry 9900) | 26% |
| Nokia Ovi Store (Nokia N8) | 26% |
| Apple App Store(iPhone 4S) | 37% |

As we can see in the table, the free software market of Android is also the biggest market.

This one is the profit of Android software market. If we want to upgrade software of smart phone, the cost will be reduced.

Table 2: Comparison free software market for each OS (Wikipedia, 2011)

Total Cost of Ownership conclusion

Now, we can summarise for Total Cost of Ownership. The TCO for HTC Thunderbolt 4G is the best. We decide base on One-Time Cost, Monthly Cost, and Additional Cost. Four types of smartphone have One-Time-Cost and Monthly Cost similar. But HTC Thunderbolt 4G Additional Cost is the best.

## Test Requirement

This WSM spread sheet model has some requirements

| Code | Requirement Name | Description |
| --- | --- | --- |
| 1 | Name: Cell validation, with appropriate instructions and error messages | This requirement applies for columns :B,C,E,H,K,N where the cell value can change by input value .the input value must be a whole number which is between 1 and 10 When user begin editing cell, show information about cell |
| 2 | Cell formatting | Many cell need to be formatted (Colour, border…); |
| 3 | Cell calculation | Values in some columns must be calculated from other columns or cells by following the WSM rule. |
| 4 | Automatic graphs | A graph is used to show comparison between four total score of each smartphone. |
| 5 | Cell protection with sheet password = “Q” | Some columns are editable by putting value (B, C, E, H, K, and N). Others are not editable because they are calculation column |
| 6 | Comments | Some cells has comment |

## Test Plan

This is test plan to check the WSM spread sheet meets the requirements or not.

| Code | Requirement Name | Test case |  | Expect result |
| --- | --- | --- | --- | --- |
|  |  | Case number | Description |  |
| 1 | Cell validation, with appropriate instructions and error messages | 1 | Input Value >10 | Show error |
|  |  | 2 | Input value <1 | Show error |
|  |  | 3 | When user begin editing cell | Show information about cell |
|  |  | 4 | Input text value | Show error |
|  |  | 5 | Input float value | Show error |

| Code | Requirement Name | Test case |  | Expect result |
| --- | --- | --- | --- | --- |
|  |  | Case number | Description |  |
| 2 | Cell formatting | 1 | Check if The WSM contains at least one cell formatted | The WSM contains at least one cell formatted |

| Code | Requirement Name | Test case |  | Expect result |
| --- | --- | --- | --- | --- |
|  |  | Case Number | Description |  |
| 3 | Cell calculation (Check expression) | 1 | Input value in two or more parameter cells, then check the value in target calculation cell is true or not by following calculation rule of WSM | Value in target calculation cell is true |

| Code | Requirement Name | Test case |  | Expect result |
| --- | --- | --- | --- | --- |
|  |  | Case Number | Description |  |
| 4 | Automatic graphs | 1 | Check if WSM spread sheet has an Automatic graphs. The graph show total score in percentage of each smartphone to compare | The WSM spread sheet has an Automatic graphs show comparison between four smartphone |

| Code | Requirement Name | Test case |  | Expect result |
| --- | --- | --- | --- | --- |
|  |  | Case Number | Description |  |
| 5 | Cell protection with sheet password = “Q” | 1 | Try to edit some non-editable cell or columns | Cannot edit |
|  |  | 2 | Check password to unprotect sheet equal “Q” | The “Q” character is the password |

| Code | Requirement Name | Test case |  | Expect result |
| --- | --- | --- | --- | --- |
|  |  | Case Number | Description |  |
| 6 | Comments | 1 | Check if the WSM spread sheet has at least one comment | The WSM sheet contains at least one comment |

## Test log

This test log checks result for the test plan, proves the WSM has met requirement.

| Code | Requirement Name | Test case |  | Status |
| --- | --- | --- | --- | --- |
|  |  | Case number | Test result |  |
| 1 | Cell validation, with appropriate instructions and error messages | 1 |  | OK |
|  |  | 2 |  | OK |
|  |  | 3 |  | OK |
|  |  | 4 |  | OK |
|  |  | 5 |  | OK |

| Code | Requirement Name | Test case |  | Status |
| --- | --- | --- | --- | --- |
|  |  | Case number | Test result |  |
| 2 | Cell formatting | 1 | Formatted cell with color, border | OK |

| Code | Requirement Name | Test case |  | Status |
| --- | --- | --- | --- | --- |
|  |  | Case Number | Test Result |  |
| 3 | Cell calculation (Check expression) | 1 | Expression: F=C*E; | OK |

| Code | Requirement Name | Test case |  | Status |
| --- | --- | --- | --- | --- |
|  |  | Case Number | Test Result |  |
| 4 | Automatic graphs | 1 | Graph shows comparison between four smartphone types | OK |

To create Auto Graph, just select a series of data by selecting some Cell, then go to tab Insert => select any type of Graph.

| Code | Requirement Name | Test case |  | Status |
| --- | --- | --- | --- | --- |
|  |  | Case Number | Test Result |  |
| 5 | Cell protection with sheet password = “Q” | 1 | Cannot edit calculation cells | OK |
|  |  | 2 |  | OK |

Steps to do Cell Protection:

- Select whole Sheet by pressing Ctrl+Shift+A

- Right Click -> Format Cells-> Protection Tab =>  UnCheck Locked

Figure 11: Cell Protection

- Select any Cell which will be locked, then Right Click=>Format Cell=>Protection Tab=> Check Locked

- Finally, go to table Review=> Protect Sheet=>, enter Password and Comfirm Password, then click OK.

Figure 12: Cell projection

| Code | Requirement Name | Test case |  | Status |
| --- | --- | --- | --- | --- |
|  |  | Case Number | Description |  |
| 6 | Comments | 1 | Figure 13: Comment | OK |

To create cell comment, select a Cell, Right Click => Insert Comment

# Appendix B- Presentation

Figure 14: Slide 1

Figure 15: Slide 2

Figure 16: Slide 3

Figure 17: Slide 4

Figure 18: Slide 5

Figure 19: Slide 6

Figure 20: Slide 7

Figure 21: Slide 8

Figure 22: Slide 9

Figure 23: Slide 10

# Appendix C- WBS

## Project Roles & Responsibilities

Project team has five members. This following table describes roles and responsibilities.

| Name | Roles | Responsibilities |
| --- | --- | --- |
| Manager | Manager of project | Project manager is the person who makes project plan, manages scope of project, and assigns work for team members and lead team members. He/she also has to do some important works. |
| Member 1 | Team Member | Member 1 is a Team member who executes some tasks |
| Member 2 | Team Member | Member 2 is a Team member who executes some tasks |
| Member 3 | Team Member | Member 3 is a Team member who executes some tasks |
| Member 4 | Team Member | Member 4 is a Team member who executes some tasks |

## Work Breakdown Structure Dictionary

This WBS Dictionary describes work details for items which are not clearly.

| WBS Item Number | WBS Item Name | Description |
| --- | --- | --- |
| 3 | Identify Problems | The Manager has to identify all existent problems in company. |
| 4 | Identify stakeholders | Stakeholders are very important. The Manager must identify stakeholders related to project then ask them all necessary question before starting project |
| 5 | Stakeholder Expectations | The manager gets all expectations of stakeholders |
| 6 | Create Project Team | Project Manager decides how many resources in order to finish the project, and then make a project team. |
| 7 | Kick-off meeting | Project team discuss together. The manager tells all problems to team members |
| 9 | Requirement for selection | In the first time of project, Project Manager has to define requirement to do selecting of smartphone type. The requirement includes of software requirement (WBS Item 10), hardware requirement (WBS Item 11) for the smartphone. The smartphone has to meet needs of company for functionality. Requirement are define in Weight Scoring Model |
| 10 | Hardware requirement | This task is subtask of WBS Item Summary 9; the manager has to define all requirements for hardware of smartphone. |
| 11 | Software requirement | This task is subtask of WBS Item Summary 9; the manager has to define all requirements for software of smartphone. |
| 12 | Write requirement documentation | After define requirement for smartphone, Project Manager has to write documentation for details of requirement. This document will be sent to all staffs in company to get all ideas. Because the project is smartphone selection and staff will use this selected smartphone. So, Project Manager makes sure that staffs want to use this phone |
| 13 | Sum up ideas of all staff | After writing requirement document, and sending it to all staff, the project manager has to sum up all staff ideas. After that, the manager will decide some type of smartphone to compare. |
| 14 | Get ideas of all staffs | In order to sum up ideas of staffs, the manager has to get all ideas from staffs. The manager can use Email or other ways, then send a document for all staffs. |
| 16 | Decide four types of smartphone | After sup up all ideas from staffs. The manager will decide four types of smartphone to make comparison in order to select one of them. |
| 17 | Write a test plan | The comparison between smartphones needs a clear plan. Each member of team can follow this plan to do the test for each smartphone. The manager will prepare for this test plan. |
| 18 | Write check list | The test plan also needs a Check List. Check list document will help the manager and team member manage, track test plan. |
| 19 | Check All Things | This is a milestone in project plan. The project team need time to summary what has been done and what will be done. |
| 21 | Buy four demo phones for testing function | After deciding four types of smartphone, the manager will buy four demo phones for each type of smartphone in order to make comparison between them. |
| 24 | Do a Weighted Scoring Model | WSM is used to compare four smartphones type by defining Factors and Criteria. The project team will test four demo smartphone and mark them. Finally, Manager calculates total mark for each smartphone. A smartphone type is selected if it has highest mark. |
| 26 | Test hardware | Project team has to test hardware of each smartphone. This is one of Factors in WSM. |
| 27 | Test software | Project team has to test software of each smartphone. This is one of Factors in WSM also. |
| 28 | Calculate the Total Cost of Ownership | Total Cost of Ownership is also one of factor in WSM. TCO means all cost to maintains smartphone after buy them. |
| 29 | Research software market | The manager has to research the software market for each type of smartphone. For example: free software, commercial software. Because it relate to TCO of each smartphone type. |
| 30 | Research all related service | The manager has to research for all services for each type of smartphone. For example: Guarantee service. Because it also relate to TCO of each smartphone type. |
| 31 | Decide a smartphone type to buy | After doing WSM , the Manager decide a smartphone type to buy for all staff |
| 32 | Check All Things | This is the second milestone in project plan. |
| 33 | Buy completed smartphone package | After doing WSM and finally select a smartphone type. The project team will buy a completed smartphone package and implement for all staffs in company. |
| 36 | Testing and find mistake phones | After receiving smartphone package, the project team has to test and find mistake phones. If there are any mistake smartphones, all of them will be changed by others by resending to the vendor. |
| 37 | Deliver phone for each staff | Each staff in company will receive a smartphone to use. The project team will deliver to all of staffs |
| 38 | Training | The manager will write a training document and send to all staffs in company. |
| 40 | Report Performance | The project manager reports to the project steering committee what has been done in order to check if there is anything change or not |
| 42 | Documenting Lessons Learned | The project manager writes a summary for this project |

## WBS Scenario

Figure 24: WBS Scenario

Figure 25: Using Notes in Project

The project plan schedule includes five common phases of all projects. The project manager use Top-Down approach to develop the project plan.

In project plan, we can view the description for each task by enable Indicator Column and view Notes like figure 12.

## WBS Details

Figure 26: WBS Details part 1

Figure 27: WBS Details part 1

## WBS Network Diagram

Figure 28: a part of Network Diagram

## WBS Critical Path

Figure 29: WBS Critical path part 1

Figure 30: WBS Critical path part 2

Figure 31: Add resource cost

Project Resource Cost

In order to calculate cost for resource in project, we can use the Bottom-Up Estimates approach. We can estimate for each individual task cost, then summing them to get the project total cost.

In MS Project, we can easily to calculate cost. We just add Resource Cost and MS Project will calculate automatically.

Now, we assume that the cost of resource for each resource type as following:

| Resource Type | Standard Cost | Over allocated Cost |
| --- | --- | --- |
| Manager | $10/hour | $20/hour |
| Team member | $8/hour | $16/hour |

In MS Project, select tab Resource=> Resource Sheet

We can see as the Figure 18. We can add resource cost for Manager and Team Member as the same way.

Figure 32: Total project resource cost is $7,760.00

# References

Smartphone Information: http://smartphones.findthebest.com/compare/96-102-103-152/Nokia-N8-vs-HTC-ThunderBolt-4G-vs-BlackBerry-Bold-9900-vs-Apple-iPhone-4S

Figure 10: Smart Phone OS Market Share (Wikipedia 2011): http://en.wikipedia.org/wiki/Smartphone

Table 2: Comparison free software market for each OS (Wikipedia, 2011): http://en.wikipedia.org/wiki/Android_Market